## CIPA FY 2025-26
PROCURING DEPARTMENT NAME: INTERNAL AUDIT
FINANCIAL YEAR: 2025/ 2026
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
TeamMate+ Annual Licence | TeamMate+ | 70000 | Annual Licence | Ongoing Contract | Service | 70000 | N/A | N/A | N/A | N/A | N/A | 7/31/2025 | 2026-07-31 | N/A
Professional fees | External Auditors | 373854 | Audit fees | Ongoing Contract | Service | 373854 | 2023-03-05 | 2024-03-31 | 2024-11-15 | 2024-07-07 | 2024-11-23 | 2024-01-04 | 2024-09-29
Capacity building | Risk Management | 100000 | Risk Management Training for the Authority | Micro Procurement | Service | 75000 | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2026-03-31 | N/A
CACS
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
| Onsite/field visits | 3600 | Meals & airtime | 3 quatations | Service | 900 | 2025-05-02 | 2025-05-06 | 2025-05-07 | N/A | 2025-05-09 | 2025-05-12 | 2025-06-30 | N/A
|  |  | Meals & airtime | 3 quatations | Service | 900 | 2025-07-07 | 2025-07-09 | 2025-07-10 | N/A | 14/7/2025 | 15/7/2025 | 2025-09-30 | N/A
|  |  | Meals & airtime | 3 quatations | Service | 900 | 2025-10-06 | 2025-10-08 | 2025-10-09 | N/A | 2025-10-10 | 13/10/2025 | 2025-12-22 | N/A
|  |  | Meals & airtime | 3 quatations | Service | 900 | 2026-01-12 | 2026-01-14 | 2026-01-15 | N/A | 2026-01-19 | 20/1/2026 | 2026-01-31 | N/A
| Workshops | 75000 | Stakeholder engagement | 3 quatations | Service | 18750 | 2025-05-02 | 2025-05-06 | 2025-05-07 | N/A | 2025-05-09 | 2025-05-12 | 2025-06-30 | N/A
|  |  | Stakeholder engagement | 3 quatations | Service | 18750 | 2025-07-07 | 2025-07-09 | 2025-07-10 | N/A | 14/7/2025 | 15/7/2025 | 2025-09-30 | N/A
|  |  | Stakeholder engagement | 3 quatations | Service | 18750 | 2025-10-06 | 2025-10-08 | 2025-10-09 | N/A | 2025-10-10 | 13/10/2025 | 2025-12-22 | N/A
|  |  | Stakeholder engagement | 3 quatations | Service | 18750 | 2026-01-12 | 2026-01-14 | 2026-01-15 | N/A | 2026-01-19 | 20/1/2026 | 2026-01-31 | N/A
| Social Media Graphic Design | 62700 | Graphic Design | 3 quatations | Service | 62700 | 2025-06-03 | 2025-06-05 | 2025-06-06 | N/A | 2025-06-09 | 2025-06-10 | 2025-09-30 | N/A
| Advertisements (newspapers) | 61046 | Advertisements | 3 quatations | Service | 15261.5 | 2025-05-02 | 2025-05-06 | 2025-05-07 | N/A | 2025-05-09 | 2025-05-12 | 2025-06-30 | N/A
|  |  | Advertisements | 3 quatations | Service | 15261.5 | 2025-07-07 | 2025-07-09 | 2025-07-10 | N/A | 14/7/2025 | 15/7/2025 | 2025-09-30 | N/A
|  |  | Advertisements | 3 quatations | Service | 15261.5 | 2025-10-06 | 2025-10-08 | 2025-10-09 | N/A | 2025-10-10 | 13/10/2025 | 2025-12-22 | N/A
|  |  | Advertisements | 3 quatations | Service | 15261.5 | 2026-01-12 | 2026-01-14 | 2026-01-15 | N/A | 2026-01-19 | 20/1/2026 | 2026-01-31 | N/A
PROCURING DEPARTMENT NAME: ADMINISTRATION AND FACILITIES
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
1 | General service | 52500 | Service of vehicles | RFQ | Supplies/ Services Works | 52500 | 2025-08-31 | 2025-09-03 | 2025-09-04 | N/A |  | 2025-09-05 | 2025-09-12 | N/A
2 | Replacement of batteries | 10000 | Batteries | RFQ | Supplies/ Services Works | 10000 | 2025-04-01 | 2025-04-04 | 2025-04-07 | N/A |  | 2025-04-07 | 2026-03-31 | N/A
3 | Replacement of Tyres | 36000 | TYRES | RFQ | Supplies/ Services Works | 36000 | 2025-04-01 | 2025-04-04 | 2025-04-07 | N/A |  | 2025-04-07 | 2025-03-31 | N/A
4 | Service of fire extinguishers for CIPA vehicles | 3600 | VEHICLE FIRE EXTINGUISHERS SERVICES | RFQ | Supplies/ Services Works | 3600 | 2025-04-01 | 2025-04-04 | 2025-04-07 |  |  | 2025-04-07 | 2025-03-31 | N/A
5 | Procurement of First Aid Kit | 1080 | FIRST AID KIT | RFQ | Supplies/Services | 1080 | 2025-04-01 | 2025-04-04 | 2025-04-07 |  |  | 2026-04-07 | 2026-03-31 | N/A
6 | Provision of Cleaning Services | 386150.52 | CLEANING SERVICES | Open Tender | Supplies/Serices Works | 386150.52 | 2025-04-01 | N/A | N/A | N/A |  | N/A | N/A | N/A
7 | Provision of Security and Alarm Monitoring Services | 685431.36 | Security and Alarm Monitoring | Open Tender | Supplies/ Services Works | 685431.36 | 2025-04-01 | N/A | N/A | N/A |  | N/A | N/A | N/A
11 | Provision of fuel Sevices to CIPA vehicles | 102000 | Fuel | Restricted/Ongoing | Supplies/Services | 102000 | 2025-04-01 | 2025-05-04 | 2025-05-07 | N/A |  | 2025-05-07 | 2026-03-31 | N/A
12 | Office Building Repairs and Maintenance | 90000 | Office Building Maintenance | RFQ | Supplies | 90000 | 2025-04-01 | 2025-05-05 | 2025-05-08 | N/A |  | 2025-05-15 | 2025-05-30 | 2025-06-05
13 | General Office Admin Expense | 33240 | General Office Admin Expense | RFQ | Supplies/Services/ Works | 33240 | 2025-04-01 | N/A | N/A | N/A |  | N/A | N/A | N/A
PROCURING DEPARTMENT NAME: FINANCE
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
2 | Corporate Subscription | 15000 | BAOA Subscription | RFQ | Services | 15000 | N/A | N/A | N/A | N/A | N/A | 2025-12-01 | 2025-12-31 | N/A
3 | Cash in Transit | 109051.92 | Cash in Transit services and its consumables | RFQ | Services | 109051.92 | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2026-03-31 | N/A
PROCURING DEPARTMNET NAME: HR
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
| Recruitment | 250000 | Recruitment | 3 quotations | Services | 250 000, 00 | continous | continous | continous | n/a | continous | 2026-04-01 | 2026-03-30 | End of Project
| End of Year& Q3 Town Hall | 200000 | End of Year& Q3 Town Hall | 3 quotations | Supplies | 200000 | 2025-03-11 | 2025-07-11 | 2025-11-11 | n/a | 2025/17/11 | 2025-01-12 | 2025-01-12 | End of Project
| Staff Wellnes activities | 129496.59 | Staff Wellness Activities | 3 quotations | Supplies | 129496.59 | 2025-03-31 | 2026-03-31 | n/a | n/a | n/a | 2026-04-01 | 2026-03-31 | End of Project
| Employee Recognition & Rewards | 40000 | Employee Recognition & Rewards | 3 quotations | Services | 40000 | 2025-06-01 | 2025-06-04 | 2025-06-06 | n/a | 2025-06-12 | 2025-07-01 | 3/31/2026 | End of Project
| Women's Day | 10000 | Women's Day | 3 quotations | Services | 10000 | 3/04/2026 | 3/10/2026 | 3/12/2026 | n/a | 3/16/2026 | 3/31/2026 | 3/31/2026 | End of Project
| Employee health & Wellness Activities | 125000 | Employee health & Wellness Activities | 3 quotations | Supplies | 125000 | 2025-03-31 | 2026/03/2026 | n/a | n/a | n/a | 2026-04-01 | 2026-03-31 | End of Project
| Psycho-social Support | 300 000, 00 | Psycho-social Support | Open Tender | Services | 300 000, 00 | 09/06/2025 | 20/06/2025 | 04/07/2025 | n/a | n/a | 10/07/2025 | 2026-03-31 | 2026-03-31
| Q4 Town Hall | 5000 | Q4 Town Hall | 3 quotations | Services | 5000 | 02/12/2026 | 02/18/2026 | 02/20/2026 | n/a | 02/24/2026 | 03/10/2026 | 03/10/2026 | End of Project
PROCURING DEPARTMENT NAME: PROCUREMENT
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
| Provision of stationery | 100000 | Supply and delivery of stationery | RFQ | Supplies | 25000 | 2025-05-19 | 2025-05-22 | 2025-05-23 | N/A | 2025-05-26 | 2025-05-26 | 2025-05-30 | N/A
|  |  | Supply and delivery of stationery (disability) | RFQ | Supplies | 25000 | 13//08/2025 | 2025-08-19 | 2025-08-20 | N/A | 2025-08-22 | 2025-08-25 | 2025-08-29 | N/A
|  |  | Supply and delivery of stationery (disability) | RFQ | Supplies | 25000 | 2025-11-21 | 2025-11-27 | 2025-11-28 | N/A | 2025-12-02 | 2025-12-03 | 2025-12-12 | N/A
|  |  | Supply and delivery of stationery | RFQ | Supplies | 25000 | 2026-02-23 | 2026-02-26 | 2026-02-27 | N/A | 2026-03-03 | 2026-03-04 | 2026-03-13 | N/A
| Provision of Refreshments | 25000 | Supply and delivery of refreshments | RFQ | Supplies | 6250 | 2025-05-19 | 2025-05-22 | 2025-05-23 | N/A | 2025-05-26 | 2025-05-26 | 2025-05-30 | N/A
|  |  | Supply and delivery of refreshments | RFQ | Supplies | 6250 | 13//08/2025 | 2025-08-19 | 2025-08-20 | N/A | 2025-08-22 | 2025-08-25 | 2025-08-29 | N/A
|  |  | Supply and delivery of refreshments | RFQ | Supplies | 6250 | 2025-11-21 | 2025-11-27 | 2025-11-28 | N/A | 2025-12-02 | 2025-12-03 | 2025-12-12 | N/A
|  |  | Supply and delivery of refreshments | RFQ | Supplies | 6250 | 2026-02-23 | 2026-02-26 | 2026-02-27 | N/A | 2026-03-03 | 2026-03-04 | 2026-03-13 | N/A
| Provision of printing & consumables | 92440 | Supply and delivery of toners | RFQ | Supplies | 30813.33 | 2025-05-19 | 2025-05-22 | 2025-05-23 | N/A | 2025-05-26 | 2025-05-26 | 2025-05-30 | N/A
|  |  |  | RFQ | Supplies | 30813.33 | 2025-11-21 | 2025-11-27 | 2025-11-28 | N/A | 2025-12-02 | 2025-12-03 | 2025-12-12 | N/A
|  |  |  | RFQ | Supplies | 30813.33 | 2026-02-23 | 2026-02-26 | 2026-02-27 | N/A | 2026-03-03 | 2026-03-04 | 2026-03-13 | N/A
| Provision of domestic Requisites | 186753 | Supply and delivery of toilet papers | RFQ | Supplies | 46688.25 | 2025-05-19 | 2025-05-22 | 2025-05-23 | N/A | 2025-05-26 | 2025-05-26 | 2025-05-30 | N/A
|  |  | Supply and delivery of domestic requisites | RFQ | Supplies | 46688.25 | 13//08/2025 | 2025-08-19 | 2025-08-20 | N/A | 2025-08-22 | 2025-08-25 | 2025-08-29 | N/A
|  |  | Supply and delivery of domestic requisites | RFQ | Supplies | 46688.25 | 2025-11-21 | 2025-11-27 | 2025-11-28 | N/A | 2025-12-02 | 2025-12-03 | 2025-12-12 | N/A
|  |  | Supply and delivery of domestic requisites | RFQ | Supplies | 46688.25 | 2026-02-23 | 2026-02-26 | 2026-02-27 | N/A | 2026-03-03 | 2026-03-04 | 2026-03-13 | N/A
PROCURING ENTITY NAME: SUSTAINABILITY
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
1 | New Francistown CIPA office Partitioning | 125000 | Partitioning of 27 metre square Francistown CIPA office | RFQ | Works | 125000 | 2025-05-01 | 2025-05-15 | 2025-06-10 | 2025-07-20 | 2025-07-30 | 2025-05-01 | 2025-08-30 | Yes
| New Francistown CIPA office architectural design | 50000 | Architectural design for the new Francistown CIPA office. | RFQ | Works | 50000 | 2025-05-01 | 2025-05-15 | 2025-06-10 | 2025-07-20 | 2025-07-30 | 2025-05-01 | 2025-08-30 | Yes
| Transfer of Human resource from Framcistown. | 30000 | Costs associated with ransfer of human resources | RFQ | Services | 30000 | 2025-05-01 | 2025-05-15 | 2025-06-10 | 2025-07-20 | 2025-07-30 | 2025-05-01 | 2025-08-30 | Yes
2 | Network setting of the new Francistown CIPA office. | 20000 | Network setting of the new Francistown CIPA office. | RFQ | Works | 20000 | 2025-05-01 | 2025-05-15 | 2025-06-10 | 2025-07-20 | 2025-07-30 | 2025-05-01 | 2025-08-30 | Yes
PROCURING ENTITY NAME: STRATEGY
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
1 | Formulation of 2027 - 2032 CIPA Strategic Plan (CIPA 3.0) | 320000 | Formulation of 2027 - 2032 CIPA 5-year Strategic Plan (CIPA 3.0) | ITT | Services (Consultancy) | 320000 | 2025-05-01 | 2025-05-15 | 2025-06-10 | 2025-07-20 | 2025-07-30 | 2025-05-01 | 2025-08-30 | Yes
2 | Conference Facility for the Formulation of 2027 - 2032 CIPA Strategic Plan | 50000 | Conferencing | RFQ | Services (Conferencing) | 50000 | 2025-05-01 | 2025-05-15 | 2025-06-10 | 2025-07-20 | 2025-07-30 | 2025-05-01 | 2025-08-30 | Yes
PROCURING ENTITY NAME: LEGAL
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
| Lexis Nexis Database | 25000 | Lexis Nexis | Direct (Renewal) | Services | 25000 | 2025-06-02 | 2025-06-09 | N/A | N?A | N/A | N/A | N/A | N/A
PROCURING DEPARTMNET NAME: IT
FINANCIAL YEAR: 2025/26
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
| Smartnet CISCO License Renewal | 120000 | Renewal of Software Licences | 3 quotations | Supplies | 120000 | 2025-09-30 | 2025-07-10 |  |  | 2025-09-10
| Veenam Backup Software | 70000 | Renewal of Software Licences | 3 quotations | Supplies | 70000 | 2026-01-30 | 2026-06-02 |  |  | 2026-10-02
| Linux Servers | 40000 | Renewal of Software Licences | 3 quotations | Services | 40000 | 7/31/2025 | 2025-11-08 |  |  | 8/13/2025
| Microsoft Office Suite | 488640.4 | Renewal of Software Licences | Open tneder | Supplies | 488640.4 | 2025-04-30 | 2025-09-05 |  |  | 5/13/2025
| Firewall Appliance for Serowe,Ftown & Maun | 114000 | Renewal of Software Licences | 3 quotations | Supplies | 114000 | 2025-12-15 | 2026-09-01 |  |  | 2026-12-01
| Verne Support & Maintenance | 8500000 | Contractual Obligation | Direct | Services | 8500000 | 2025-03-19 | 19/042026 |  |  | 3/19/2025
| ACCPAC & VIP Software | 160000 | Renewal of Software Licences | 3 quotations | Services | 160000 | 1/28/2026 | 2026-05-02 |  |  | 2026-09-02
| BI License | 150000 | Purchase of software | 3 quotations | Services | 150000 | 2026-02-28 | 2026-09-03 |  |  | 2026-11-03
| PRTG | 114000 | Renewal of Software Licences | 3 quotations | Supplies | 114000 | 2026-02-28 | 2026-09-03 |  |  | 2026-11-03
| Vmware | 385000 | Renewal of Software Licences | Open tneder | Services | 385000 | 2026-02-03 | 2026-12-02 |  |  | 2/16/2026
| WS02 |  | Renewal of Software Licences | Direct | Services | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MSSQL 2019 Enterprise Core license | 70000 | Renewal of Software Licences | RFQ | Supplies | 70000 | 10/30/2025 | 2025-07-11 |  |  | 2/18/2026
| Internal Audit Software (ACL) Licence | 70000 | Renewal of Software Licences | 3 quotations | Services | 70000 | 2025-05-30 | 2025-09-06 |  |  | 2025-10-06
| Sophos Endpoints | 188500 | Renewal of Software Licences | 3 quotations | Services | 188500 | 30/02/2026 | 2026-10-03 |  |  | 2026-12-03
| Sophos Servers | 223300 | Renewal of Software Licences | 3 quotations |  | 223300 | 30/02/2026 | 2025-07-03 |  |  | 2026-10-03
| SMS Notifications | 400000 |  | Tender | Supplies | 400000 | 2025-01-30 | 2025-02-14 | 2025-02-25 | 2025-02-27 | 2025-03-04 | 2025-03-24 | 2027-03-24 | End of Activity Report
| PMS | 71500 |  | 3 quotations | Services |  | 2025-12-12 | 12/22/2025 | n/a | n/a | 2026-08-01 | n/a |  | End of Project
| Security Support (CCTV and Access control) - Maintenace ans spares | 229992 | Renewal of Software Licences | RFP | Supplies | 229992 | 2026-03-15 | n/a | n/a | n/a | n/a | n/a |  | End of Project
| Fire Suppression System | 15000 |  | 3 quotations | Services | 15000 | 2025-08-30 | n/a | n/a | n/a | n/a | n/a |  | End of Project
| UPS Maintenance | 120000 |  | 5 quotations | Supplies | 120000 | 2025-09-30 | n/a | n/a | n/a | n/a | n/a |  | End of Project
| Firewall security controls-Wifi Access Point,including Pheripherals and Network Equipment | 158000 |  | 5 quotations | Services | 158000 | 2025-12-15 | n/a | n/a | n/a | n/a | n/a |  | End of Project
| Document Bank(Offsite Backup and Storage | 22200 |  | 3 quotations | Services | 22200 | ONGOING | n/a | n/a | n/a | n/a | n/a |  | End of Project
| Network Switch | 30000 | 30000 | 3 quotations | Supplies | 30000 | 2025-01-30: 2026-03-12; 2025-02-14: 2026-02-19; 2025-03-04: 2026-02-21

## MEMBERSHIP
PROCURING ENTITY: CIPA
FINANCIAL YEAR: 2025/ 2026
Professional membership fees | BICA Membership | 5189 | Statutory professional membership requirement | Direct Procurement | BICA | 5189 | N/A | N/A | N/A | N/A | N/A | 2025-12-01 | 2025-12-31 | N/A | Membership paid annually every December | BICA | 5189
Professional membership fees | IIA Membership | 3200 | Statutory professional membership requirement | Direct Procurement | IIA Botswana | 3200 | N/A | N/A | N/A | N/A | N/A | 2026-03-01 | 2026-03-31 | N/A | Membership paid annually every March | IIA Botswana | 3200
Professional membership fees | ACCA Membership | 5607 | Professional membership requirement | Direct Procurement | ACCA | 5607 | N/A | N/A | N/A | N/A | N/A | 2025-12-01 | 2025-12-31 | N/A | Membership paid annually every December | ACCA | 5607
Professional membership fees | ISACA Membership | 2750 | Professional membership requirement | Direct Procurement | ISACA | 2750 | N/A | N/A | N/A | N/A | N/A | 2025-12-01 | 2025-12-31 | N/A | Membership paid annually every December | ISACA | 2750
Professional membership fees | CIPS Membership Fees | 6240 | Professional membership requirement | Direct Procurement | Service | 6240 | [8 empty] | Membership paid annually | CIPS
Professional membership fees | CIS Subscription | 6000 | Professional membership requirement | Direct | Services | 6000 | 2025-12-01 | 2025-12-08 | N/A | N/A | N/A | N/A | N/A | N/A | Membership paid annually | Chartered Governance Institute of Southern Africa | 6000
Professional membership fees | Various Finance team memnebership | 62856 | Professional membership requirement | RFQ | Services | 62856 | N/A | N/A | N/A | N/A | N/A | 2025-12-01 | 2026-01-31 | N/A | Membership paid annually